## Sheet1
Rank | Item
1 | As a user, I want to be able to create a profile in order to create comment on posts.
2 | As a user, I want to be able to view posts without logging in.
3 | As a user, I want to track my workouts in my profile.
4 | As a user, I want to to view and sing-up for events.
5 | As a user, I want to make a request to an admin to create an event.
6 | As a user, I want to search for other members.
7 | As a user, I want to send and receive private messages with other members.
DAY | LOGS
22/11 | 1) After sprint planning meeeting, the product backlog was commited into product backlog items (user stories) and prioritized them by desired functionality
2) For each user story were created several tasks in order to achieve definition of done.
3) Network diagram.
24/11 | Scrum board
[6 empty] | Activity | Predecessor | Duration (days)
[6 empty] | A | / | 3
[6 empty] | B | A | 2
[6 empty] | C | B | 2
[6 empty] | D | A | 2
[6 empty] | E | A | 2
[6 empty] | F | E,G | 1
[6 empty] | G | E | 1
[6 empty] | H | E | 3
[6 empty] | I | A | 1
[6 empty] | J | I | 1
[6 empty] | K | J | 3
|  | 1 | A | Implement login functionality | Sprint 1 |  |  | Sprint 1 | Commited backlog items | Tasks not started | Tasks in progress | Tasks Completed
|  | 2 | B | Implement posts | Sprint 1
|  |  | C | Implement comments | Sprint 2
|  | 3 | D | Tracking workouts of each user | Sprint 1
|  | 4 | E | List of events | Sprint 1
|  |  | F | Sign-up for an event | Sprint 2 |  |  | Day 1
|  |  | G | View Event | Sprint 2 |  |  | 22/11
|  | 5 | H | Make a request to admin to create an event | Sprint 2
|  | 6 | I | List of all members | Sprint 1
|  |  | J | Search for a specific member | Sprint 2
|  | 7 | K | Send/receive private messages between users | Sprint 2
[8 empty] | Sprint 1 | Commited backlog items | Tasks not started | Tasks in progress | Tasks Completed
Day 2
24/11
[9 empty] | Commited backlog items | Tasks not started | Tasks in progress | Tasks Completed
Sprint 2
Day 3
02/12
[9 empty] | Commited backlog items | Tasks not started | Tasks in progress | Tasks Completed
Sprint 2
Day 3
09/12
[9 empty] | Commited backlog items | Tasks not started | Tasks in progress | Tasks Completed
Sprint 2
Day 3
16/12